## TIMELINE SUMMARY
October 2023 | Prepare grant request
Submit grant request
November 2023 | Establish event committee and hold initial planning meeting
Hold zoom meeting with leadership of chorus
Select music for festival chorus - 2 songs
Purchase music and learning tracks as needed
Secure demonstration quartet(s)
Investigate and secure venue(s); pay deposit (roadshow chorus to secure appropriate venue)
January 2024 | Order sound equipment as needed (roadshow chorus will order for their location)
Prepare flyers and registrations informations and forms
Contact middle and high school music educators and schedule a time to visit classrooms. (Provide materials and guidance to roadshow chorus)
Order printed swag
Prepare schedule for the day
February 2024 | Marketing - contact local magazines, papers (provide materials and guidance to roadshow chorus)
Prepare waivers and COVID protocols
Finalize and print registrations information/flyers for distribution to classrooms and other
March 2024 | Marketing - contact local radio stations (provide materials and guidance to roadshow chorus)
Second contact with middle and high school music educators
Contact area Girl Scout troops and 4-H clubs (provide materials and guidance to roadshow chorus)
Prepare classes
April 2024 | Third contact with music educators
Secure QR Code for registrations
Create events and distribute events on social media; pay for upgrades/promotion (provide guidance to roadshow chorus)
Create tri-fold promotion flyer to distribute at events
Prepare COVID release as needed
Music and learning track distribution to registered participants
Arrange for photographer (roadshow chorus to provide their own)
Each chorus involved to develop promotional materials for themselves
Finalize classes, prepare schedule, prepare script
May 2024 | Distribute waivers
Final contact with music educators
Marketing - communicate with all print and air media outlets (provide materials and guidance to roadshow chorus)
Evaluate COVID situation at each location
Assign teams to set up and tear down; plan for lunch and water during the day (roadshow chorus to provide their own)
June 2024 | Finalize participant list
Print hard copies of music for at the door
Print tri-fold promotional flyers for at the door
Print COVID release forms as needed

## TIMELINE DETAILS
Month | Task | Due Date | Assigned To | Date Completed | Notes
October 2023 | Prepare grant request | 2023-11-01 |  | 2023-10-31
| Submit grant request | 2023-11-01 |  | 2023-10-31 | Received notice that we were awarded a $ grant.
November 2023 | Establish event committee and hold initial planning meeting | 2023-11-01 |  |  | Committee members:
| Hold first committee meeting - zoom | 2023-11-01 | Committee | 2024-03-03
| Select music for festival chorus - 2 songs | 2023-11-01 | Committee | 2024-03-03
| Purchase music and learning tracks as needed | 2023-11-01 |  | 2024-03-03
| Secure demonstration quartet(s) | 2023-11-01 |  | 2024-03-03
| Investigate and secure venue(s); pay deposit | 2023-11-01 |  | 2024-03-03 | local methodist church
January 2024 | Secure sound equipment as needed | 2024-04-20 |  | 2024-04-21
| Prepare flyers and registrations informations and forms | 2024-04-20 |  | 2024-04-21
| Contact middle and high school music educators and schedule a time to visit classrooms. (Provide materials and guidance ) | 2024-04-20 |  | 2024-04-21
| Order printed swag | 2024-04-20 |  | 2024-04-21 | t shirts and bag
| Prepare schedule for the day | 2024-04-20 |  | 2024-04-21
February 2024 | Marketing - contact local magazines, papers (provide materials and guidance to roadshow chorus), news release, community calendars | 2024-04-20 |  | 2024-04-21
| Prepare waivers and COVID protocols | 2024-04-20 |  | 2024-04-21
| Finalize and print registrations information/flyers for distribution to classrooms and other | 2024-04-20 |  | 2024-04-21 | Reviewing to make sure SAI acknowledgement and logo are included.
March 2024 | Marketing - contact local magazines, papers (provide materials and guidance to roadshow chorus), news release, community calendars | 2024-04-20 |  | 2024-04-21
| Second contact with middle and high school music educators | 2024-04-20 |  | 2024-04-21
| Contact area Girl Scout troops and 4-H clubs (provide materials and guidance to roadshow chorus) | 2024-04-20 |  |  | Flyer specific to Girl Scouts has been developed.
| Prepare classes | 2024-04-20 |  | 2024-04-21
April 2024 | Third contact with music educators | 2024-04-20 |  | 2024-04-21
| Secure QR Code for registrations and set up registration | 2024-05-19 |  | 2024-04-21
| Create events and distribute events on social media; pay for upgrades/promotion | 2024-05-19
| Create tri-fold promotion flyer to distribute at events | 2024-05-19 |  | 2024-04-21
| Prepare COVID release as needed | 2024-05-19 | Committee | 2024-04-21
| Music and learning track distribution to registered participants | 2024-05-19
| Arrange for photographer | 2024-05-19
| develop promotional materials for chorus(es) involved | 2024-05-19
| Finalize classes, prepare schedule, prepare script | 2024-05-19 | Educators | 2024-04-21
| Travel planned and funded (region 8 and SAI for possible funds) | 2024-05-19 | Educators and others
| Lunch - provide or no | 2024-05-19
| Follow up on T-shirts / bags | 2024-05-19 |  | 2024-04-21
| Assign teams to set up and tear down; plan for water and snacks | 2024-05-19
May 2024 | Hold planning meeting for final details | 2024-05-19
Distribute waivers
Final contact with music educators
Marketing - contact local magazines, papers (provide materials and guidance to roadshow chorus), news release, community calendars
Evaluate COVID situation at each location
June 2024 | Finalize participant list
Print hard copies of music for at the door
Print tri-fold promotional flyers for at the door
Print COVID release forms as needed
Confirm with needed volunteers
Confirm with faculty

## ADVERTISING & MARKETING
BUSINESS | TYPE | POSTER | NEWS RELEASE | OTHER
EVENTBRITE | CALENDAR | X
WEBSITE | CALENDAR | X
KAFM | CALENDAR | X
CHAMBER OF COMMERCE | CALENDAR | X
VISIT CITY | CALENDAR | X
LOCAL NEWSPAPER | CALENDAR | X
LOCAL GROCERY BULLETIN BOARD | CALENDAR | X
PALISADE CITY | CALENDAR | X
DISTRICT 51 TEACHERS
DISTRICT 50? TEACHERS
COLLEGE MUSIC GOUPS
GIRL SCOUTS
4H
DAILY SENTINEL | CALENDAR | X

## DAY SCHEDULE
Grand Mesa A Cappella Youth Festival
2024-07-13
Start Time | Activity | Song | Minutes | Run By | Details/Notes
10:00am | Introduce group |  | 5 |  | Why we are here!
10:05am | Physical warm-ups |  | 10 |  | Chorus leading
10:15am | Vocal warm-ups |  | 25 |  | alignment, breathing, resonance.
10:40am | Opening Song |  | 5
10:45am | Class Instruction |  | 10 |  | HIstory of Barbershop
10:55am | Class Instruction | One Song At A Time (B♭) | 25 |  | BBS Balance & Part Characteristics w/demo quartet
11:20am | Section rehearsal | One Song At A Time (B♭) | 25 |  | Quartet
11:45am | Duet Sectionals | One Song At A Time (B♭) | 20 |  | Quartet
12:05pm | Lunch |  | 50 |  | Lunch - provided
12:55pm | Class Instruction |  | 15 |  | How to Take a Pitch
1:10pm | Section rehearsal | You've Got a Friend In Me | 25
1:30pm | Duet Sectionals | You've Got a Friend In Me | 20
1:55pm | Rehearse song | You've Got a Friend In Me | 50
2:45pm | Class Instruction |  | 15 |  | Health Benefits of Singing
3:00pm | Stretch Break
3:05pm | Rehearse song | One Song At A Time (B♭) | 30
3:30pm | Chorus Rehearsal | One Song At A Time (B♭) | 20
3:50pm | Chorus Rehearsal | You've Got a Friend In Me | 20
4:10pm | Break |  | 20 |  | show prep
Performance begins at 4:30pm
Performance Schedule
4:30pm | Opening Song | Optimistic Voices | 5 |  | Chorus leading
4:35pm | Introduce group |  | 5
4:40pm | Perform Set | One Song At A Time (B♭) | 5 |  | Harmony Festival Group
4:45pm | Introduce group |  | 2
4:47pm | Perform Set | two songs | 10 |  | DejaKind
4:57pm | Introduce group |  | 2
4:59pm | Perform Set | April Showers | 10 |  | Chorus leading
Sunny Side of the Street
5:09pm | Introduce group |  | 2
5:11pm | Perform Set | Orange Colored Sky | 3
5:14pm | Introduce group |  | 2
5:16pm | Perform Set | Come on and Sing | 3 |  | Chorus leading
5:19pm | Introduce group |  | 2
5:21pm | Perform Set | You've Got a Friend In Me | 5 |  | all participants
5:26pm | Introduce song |  | 2 |  | closing
5:28pm | Closing Song | How We Sang Today | 8
As of July 11, 2024

## VOLUNTEERS
NAME | TASK | DESCRIPTION
| PVI's | Friday evening PVIs: 7:30-9:00pm, $10 charge which helps fund event
| Registration Table | Participant List, Name badges
Class
| PVI's | Friday evening PVIs: 7:30-9:00pm, $10 charge which helps fund event
| Transportation | transport guests as needed
| Set up / Take Down | Arrive 9am to set up risers, chairs and rooms, risers will go to sanctuary for show at 4pm, then put away
| Set up / Take Down | Arrive 9am to set up risers, chairs and rooms, risers will go to sanctuary for show at 4pm, then put away
| Equipment | Projector and Screen and blue tooth speaker
| Marketing | Instagram, email educators,
| Marketing | Poster, print poster, distribute etc.
| Marketing | tri fold flyer
| Marketing | Show Flier - to promote show
| Music | Purchase You've Got A Friend for chorus
| PVI's | Friday evening PVIs: 7:30-9:00pm, $10 charge which helps fund event
| Marketing | Place add with Daily Sentinel, send out news releases: add $450 (grant $400, GMAC $50)
| Event Photos | SAI Grant requires event photos be submitted for marketing use
| Meal | water for the day, lunch: sliders, chips, cookies, soda
| Set up / Take Down | Arrive 9am to set up risers, chairs and rooms, risers will go to sanctuary for show at 4pm, then put away
| Transportation | transport guests as needed
Class
| PVI's | Friday evening PVIs: 7:30-9:00pm, $10 charge which helps fund event
| Class | History of SAI
| PVI's | Friday evening PVIs: 7:30-9:00pm, $10 charge which helps fund event
| Meal | water for the day, lunch: sliders, chips, cookies, soda
| Marketing | Facebook
| Emcee | Emcee Show at end of day
| Equipment | Sound Equ for day plus show
| Membership Table | Set up table with information about GMAC Membership: biz cards, tri fold flyers, poster on tripod, etc.
| Membership Table | Help volunteer
| Registration Table | Work with volunteer to check people in.
| Music | Teach
| Grant | Apply for and track grant
| Set up / Take Down | Arrive 9am to set up risers, chairs and rooms, risers will go to sanctuary for show at 4pm, then put away

## GRANT BUDGET DETAIL
HPHC Festival Grant |  |  | As of July 2, 2024 |  | = submitted
| 2024 HPHC FESTIVAL | EXPENSE (INCOME) |  |  | = members must submit
June | Advertising | 340 | Ads in NOCO Style ($340)-pd 4/12/24 |  | =received or will receive shortly
July | Advertising | 450 | city
July | Consumables | 200 | lunch
July | Equipment | 200 | sound and visual
July | Facility | 250 | facility rental
July | Faculty | 500 | quartet and faculty ($100 for 5 people)
July | Lodging | 978 | 2 rooms/2 nights - quartet
July | Lodging | 489 | 1 room/2 nights - clinician |  | 15.3035 | = Cost/t-shirt
May | Music | 50 | 10 copies-You've Got a Friend-BHS Download
June | Swag | 129.54 | bags
June | Swag | 474.51 | t-shirts
July | Printing/Publicity | 198.4 | printing
July | Travel | 212.8 | est mileage $0.35
July | Travel | 175 | Est mileage 2 people 500 miles R/T $0.35
July | Travel | 175 | Est mileage 2 people 500 miles R/T $0.35
T-shirts?
| TOTAL EXPENSES | 4822.25
*Feb 23* | SAI GRANT | -2400 | Rec'd 80% of $3000 grant
| BALANCE DUE AFTER GRANT | 2422.25
| Refund for NOCO Ad not used | -125 | refund from _
| Region 8 YWIH Funding | -474 | Regional fund
| Remaining Grant Funds | -600
| International Travel | 0 | one vehicle 608 mlilesR/T at $0.65/mile
| Regional Travel | 0 | 2 vehicles at $0.35/mile
| T-shirts | -76.5177 | t-shirts purchased by chorus members | may not happen b/c of # of participants
| Equipment donations | -200 | chorus
| ad donation | -50 | chorus
| printing donation | -198.5 | individual purchase
| TOTAL | -1724.0177
| Amount (over)/under-funded | 698.2323

## EXP SUMMARY
HPH FESTIVAL EXP SUMMARY |  | City
EXPENSE | AMOUNT | NOTE
FACILITY | 250 | RUMC | TOTAL EXPECTED EXPENSES | 4843.72
FACULTY | 600 |  | TOTAL IN'T REIMBURSEMENTS | -1445.32
TRAVEL | 480.77 |  | TOTAL OTHER DONATIONS | -448.4
TRAVEL | -480.77 | INT'L |  | 2950
TRAVEL | 399.55
TRAVEL | -399.55 | INT'L
TRAVEL | 565
TRAVEL | -565 | INT'L
LODGING | 1500
EQUIPMENT SOUND | 100
EQUIPMENT SOUND | -100 | DONATION
EQUIPMENT VISUAL | 100
EQUIPMENT VISUAL | -100 | DONATION
CONSUMABLES | 200 | MEAL
ADVERTISING | 450
ADVERTISING | -50 | DONATION
PRINTING / PUBLICATIONS | 198.4
PRINTING / PUBLICATIONS | -198.4 | DONATION
2950
ENROLLMENT AS OF 6/13/2024
CHORUS MEMBERS | 20
NON CHORUS MEMBERS | 13

## REGISTRATION SHEET
# | Check In, Initials | Minor | Multiple tickets purchased | Photo permission | Last name | First name | Email | Phone / Text | Parent / Guardian Name if under 18 | Parent / Guardian Phone / Text | Are you involved in Girl Scouts or another women's group? | What part do you sing? | How did you hear about the Festival?
77
78
79
80
81
82
83
84
85
86
87
88
89